**Specialty Pathways and Action Plan for COVID-19 - Surg Plan**



Semi - Elective Surgery action: vascular access

|  |  |  |
| --- | --- | --- |
| Action | Owner | Date |
| Review patients booked – cancel those who can wait 3 to 4 months | Dr Lawman | 19/03/2020 |
| Convert pts who were to have blocks if possible to LAs | Dr LAwman | 19/03/2020 |
| Majority of cases are day cases via renal day case unit – if day case unit required for decant of pts due to COVID19 then these will be cancelled | Dr lawman | 19/03/2020 |
| Cases requiring admission only to be done if urgent | Dr lawman | 19/03/2020 |
|  |  |  |

Elective Surgery pathway

Emergency pathway action: renal access

EG

|  |  |  |
| --- | --- | --- |
| Action | Owner | Date |
| renal emergency pathway – pts will be admitted to renal ward ideally direct from renal opd area | Dr LAWman/ Mr El SAkka | 19/03/2020 |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Elective Surgery pathway

Outpatients

EG

|  |  |  |
| --- | --- | --- |
| Action | Owner | Date |
| Consider Telephone clinic appointments for all vascular access pts | Dr Lawman | 19/03/2020 |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Outpatients pathway – all come through renal

Diagnostics

EG

|  |  |  |
| --- | --- | --- |
| Action | Owner | Date |
| Vascular scanning to be done on level 8 for the few pts when urgent | Dr LAwman | 19/03/2020 |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Pathway

Equipment

Any essential requirement that maybe required due to COVID-19 – no additional equipment

Staffing

* Including access problems for patients that are in London
* Using SPA for consultant time
* Changes to rotas to manage

No issues currently