## Sheet1
WRES Action Plan
Agreed by WRES Working Group June/July 2018
2018-2021
ONE | Issue: BME applicants appear to be less successful through our recruitment processes than White applicants
What is already in place? Shortlisting through TRAC requires rationale for shortlisting. Interview assessment sheets require scoring. At least 2 people required to shortlist.
| Actions required | Outcome | WRES indicators | Theme(s) | Lead | Timescale | Progress notes
1.1 | All Band 7 and above posts to have diverse interview panels. | Better BME representation throughout the higher bands within BSUH. | 2, 7 | Recruitment & Training | Abbi Denyer /Babs Harris | 2021-10-01 | First cohort of trained staff to undertake interviews early January 2021. These interview panels will where possible include the diversity that represents BSUH
1.2 | Values Based Recruitment to be implemented, | To achieve a fair and equitable recruitment process. | 1, 2, 7 | Recruitment & Selection | Abbi Denyer | Completed | Initial use of diversity flashcards has been succesful. Now being rolled out for wider usage
1.3 | Monitor, review and publish the recruitment monitoring data. | To achieve a fair and equitable recruitment process and ensure no blockages in any areas. | 2, 7 | Recruitment & Training | Abbi Denyer | Completed | Continues to be published annually via our Workforce Race Equality Standard (since 2015). 1.1 and 1.2 are outcomes of this action. HR are now providing more detailed reports that are looking at why there are the differences we are seeing in our WRES data
1.4 | Offer BME staff career development support and interview skills training. | To develop training opportunities for BME staff to aid their career development. | 4,7 | Education & Training | Abbi Denyer/Babs Harris |  | Opportunities have been highlighted for BME staff via initiatives from KSS Leadership Academy. Ongoing engagement with BAPIO and Learning and Development
1.5 | Recruitment images to be representative of population. | To actively encourage a greater diversity of applicants. | 2, 7 | Recruitment & Training | Abbi Denyer/Neil Hopkins | Completed | The Comms Lead for this is now Tasha Gardner. In all promotional and team engagements, we are ensuring a greater diversity of our workforce are represented.
TWO | Issue: Staff from BME groups appear more likely to be subject to formal processes than White staff
What is already in place? HR spreadsheet records all formal processes and this is recorded also on ESR
| Actions required | Outcome | WRES indicators | Theme(s) | Lead | Timescale | Progress notes
2.1 | Ensure that Trust policies are equally applied to all staff. | Fairness in the application of all policies regardless of race. | 3, 8 | Communication & Training | Babs Harris | Ongoing on 3 year cycle | HR Policies, Health and Safety, Risk Management and Quality Safety Policies are routinely checked using our Due Regard process. Trust wide programme will commence in April 2020 to ensure that all policies etc follow this process.
2.2 | Ensure that those staff in leadership roles throughout the organisation are equipped to understand the complexities of race equality. | Greater understanding and knowledge of the impact of race discrimination. Reduction in racial discrimination cases. | 3, 6, 8 | Communuication, Appraisal & Education | Abbi Denyer/Kali Varadarajan/Babs Harris | May/June 2020 | First cohort to undertake this will be May/June 2020. Allowing sufficient time for commissioning/procurement etc.
THREE | Issue: Throught the staff survey BME staff report higher levels of bullying, harassment or abuse from colleagues/managers than White staff
What is already in place? Freedom to Speak Up Guardian, HELP Service, Working Together Effectively
| Actions required | Outcome | WRES indicators | Theme(s) | Lead | Timescale | Progress notes
3.1 | Initiate conversations in training and include equalities discrimination and bullying concerns within the remit of the Freedom to Speak Up Guardian. | Internal material to be developed. Staff better understand the role of the Freedom to Speak Up Guardian. | 5, 6 | Communication, Education & Training | Babs Harris/Caroline Owens | Completed | FTSUG has now a slot on Induction and continues to be at many Trust training events.
3.2 | Highlight what our zero tolerance approach is. | Education through posters, online learning, messages from senior leaders. | 5 | Training | Babs Harris/Kali Varadarajan | May/June 2021 | Joint work with WRES Working Group, members of HR Policy Group and Learning and Development is being undertaken
FOUR | Issue: A higher percentage of BME staff report experiencing discrimination at work in the last 12 months
What is already in place? Equality, Diversity and Inclusion Policy; Equality and Diversity session at Corporate Induction and as part of Mandatory training programme. Due Regard within workforce policies.
| Actions required | Outcome | WRES indicators | Theme(s) | Lead | Timescale | Progress notes
4.1 | Roll out the 'No Bystanders' film. (Re-named "What you permit you promote" | An organisational understanding of the impact discrimination can have. | 8 | Education & Training | Tasha Gardner/Babs Harris | Completed | An initial 4 short films have been produced, BSUH film will be in draft format May 2020
4.2 | Update the Violence and Aggression Policy. | Current policy will be updated to ensure relevant to current issues. | 5 | Training & Communication | Abbi Denyer | Completed | This policy has been updated and approved by TEC. Recommendations followed and equipment purchased and training undertaken.
4.3 | Look into unconscious bias or cultural intelligence awareness training/education. | A greater understanding of what can lead to unintentional misunderstandings in teams/departments. | All excluding 9 | Education, Training & Communication | Babs Harris/Kali Varadarajan | May/June 2021 | This is part of the suite of services that will be commissioned to support 1.1 and 2.2